## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Project Team |  | Knowledge-gap records were missing a user_id column, which prevented knowledge gaps from being fully user-specific. | M4 | Project Team | Logical | Added an Alembic migration to add user_id to knowledge_gaps and wired the model/foreign-key relationship. |  | Closed | Migration e9b7e767c397_add_user_id_to_knowledge_gaps.py is included in the project.
2 | Project Team |  | Failed login credentials could be obscured by the global initial-session loading state, reducing visibility of authentication errors. | M3 | Project Team | User Interface | Adjusted AuthContext login handling so normal login does not toggle the initial session-verification loading state; authentication errors remain visible. |  | Closed | PROJECT_GUIDE.md documents the corrected login error UX.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others